**Tasks Description Document**

**Links for Project**

**Link for coding (Google Colab):**

<https://colab.research.google.com/drive/1FBlonoql2cvPY-RDAmC9XPFUaI6j2esW?usp=sharing>

**Link for Writing (Overleaf):**

To be provided by Jonathan

**Responsibilities**

The entire team will be responsible for making sure that the entire code is done, but some selected people are responsible for particular tasks. Responsibility can be inferred from the order of name arrangement and colours.

**Coding**

**Yuqi**

**Andrew**

**Darsh**

Nuhu

Jonathan

Huajie

**Coding Review**

**Darsh**

**Writing**

**Jonathan**

**Huajie**

**Nuhu**

Darsh

Andrew

Yuqi

**Writing Review**

**Nuhu**

**Project Management**

**Jonathan**

**Nuhu**

**Meeting Times**

Mondays 10 am

Tuesdays during Text Mining Lab

**Deadliness**

**Coding**

1st Draft (Colab): Saturday 6th March – Yuqi and Andrew

2nd Draft (Reviewed Notebook): 7th March – Darsh

3rd Draft (.py file): 8th March – Darsh, Andrew and Yuqi

Final Draft: 10th March – All members

**Writing**

1st Draft (Overleaf): Tuesday 9th March – Jonathan and Huajie

2nd Draft (Reviewed Overleaf): 10th March – Nuhu

Final Draft: 11th March – All members

**Final Draft:**

12th March (12pm) – All members

**Final Submission**

Nuhu (12th March before 10pm)